## project
Thesis Planning
[7 empty] | Plan |  |  | Actual |  |  | Delays
| ACTIVITY | START | DURATION | WEEKS
|  |  |  | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1 | Literature Analysis | 2015-11-09 | 5 weeks | bar: WEEKS 46 to WEEKS 51
2 | Writing graduation plan | 2015-11-30 | 5 weeks | bar: WEEKS 49 to WEEKS 1
3 | Prepare P2 presentation | 2016-01-11 | 1 week | bar: WEEKS 2
4 | Collect data | 2015-11-09 | 4 weeks | bar: WEEKS 46 to WEEKS 50
5 | Converting static data to RDF | 2015-12-07 | 4 weeks | bar: WEEKS 50 to WEEKS 53; WEEKS 2; WEEKS 7
6 | Method to link data sets | 2016-01-11 | 3 weeks | bar: WEEKS 2 to WEEKS 3; WEEKS 8 to WEEKS 9
7 | Create WPS to publish linked data | 2016-02-01 | 3 weeks | bar: WEEKS 3 to WEEKS 4; WEEKS 9 to WEEKS 10
8 | Method to query data sets | 2016-02-29 | 4 weeks | bar: WEEKS 5 to WEEKS 6; WEEKS 11 to WEEKS 12
9 | Create WPS to query linked data | 2016-02-08 | 4 weeks | bar: WEEKS 6; WEEKS 12 to WEEKS 13
10 | Write thesis first draft | 2016-01-25 | 13 weeks | bar: WEEKS 4 to WEEKS 17
11 | Prepare P4 presentation | 2016-05-02 | 1 week | bar: WEEKS 18
12 | Improve thesis first draft | 2016-05-09 | 5 weeks | bar: WEEKS 19 to WEEKS 23
13 | Prepare P5 presenation | 2016-06-13 | 1 week | bar: WEEKS 24
| P1 Presentation | 2015-11-10 | 1 day | bar: WEEKS 46
| P2 Deadline | 2016-01-10 | 1 day | bar: WEEKS 1
| P2 Presentation | 2016-01-18 | 1 day | bar: WEEKS 3
| P3 Presentation | unknown | 1 day
| P4 Deadline | 2015-05-02 | 1 day | bar: WEEKS 17
| P4 Presentation | 2015-05-09 | 1 day | bar: WEEKS 19
| P5 Deadline | 2015-06-13 | 1 day | bar: WEEKS 23
| P5 Presenation | 2015-06-20 | 1 day | bar: WEEKS 25
| Other project | 2015-11-17 | 3 days | bar: WEEKS 47
| Christmas Holidays | 2015-12-23 | 1.5 weeks | bar: WEEKS 52 to WEEKS 53